Annex "D and E"

ANNEX "D"-SERVICE-FEE SCHEDULE

T1: OPERATING FEE:

After the first mobilization is completed and the operability of the material together with the entire team specified in the contract and its annexes is approved in writing by the representative of the Operator and "Accepted", the Contractor is notified and the drill is connected and starts.

The T1 operating fee ends with the completion of the well program of the Operator, string dismantling, dismantling of the wellhead, cleaning of the tanks, after which the T5 transportation fee applies. In order for the T1 operating fee to start again at the end of the next transportation and installation, the transportation and installation must be completed completely and without any problems and the contractor must have fulfilled all responsibilities including mud pit emptying and cleaning at the previous location.

T2: STANDBY FEE WITH THE TEAM:

Upon notification by the Operator to the Contractor at the workplace that the service cannot be received for a valid reason, 90% of the operating fee (T1) is paid. The Operator does not need to notify the Contractor in advance for the cost of waiting with the team.

In the event that the Operator cannot indicate a new location for the next well where activities will be started during the transportation process between two wells (between release and spud) within the scope of this Agreement, for various reasons; after the signed report that preaper stating that the demobilization is completed and approved by the Operator;

No payment will be made to the Contractor in case of location waiting of up to 3 days,

If the waiting period exceeds 3 days, the location waiting fee for the period exceeding 3 days is paid as explained below.

After the signed report prepared by the Contractor stating that the demobilization is completed and approved by the Operator, 50% of the T1 operating fee is calculated over 24 hours and paid to the Contractor for the period between the end date of the demobilization (not included) and the date when the Operator notifies the new location (not included) for the start of intermobilization.

In the event that the Contractor wins a new tender with a rig operating under this contract, the Contractor may not claim any fee for the delays caused by the Operator in this process (the period between the end date of the activities under the current contract and the start date of the activities under the new contract), and no fee shall be paid to the Contractor by the Operator under any circumstances.

T3: MAINTENANCE FEE:

For each rig, the Operator shall pay the Contractor a maintenance fee of 85% of the operating fee (T1) provided that the repair of the Contractor's tools, equipment or machinery does not exceed 24 (twenty-four) hours during 1 (one) calendar month. The Contractor shall not be paid by the Operator for repair time exceeding 4 hours in a calendar day and/or repair time exceeding 24 hours in a calendar month. When determining the rig repair fee, the services received by the Contractor from 3rd parties shall be considered as part of the rig.

Daily lubrication and routine maintenance work on the rig shall not be referred to as "repair" and the Contractor shall not devote more than 0.5 hours in total per working day to these services.

T4: FORCE MAJEURE FEE:

It is paid as 60% of the operating fee (T1) under the following conditions.

Natural disasters, state of war (actual or undeclared), rebellion, revolution, terrorist activities, activities of the state or state organs (legal proceedings, court, etc.), explosions, work stoppages due to work accidents, extreme adverse weather conditions or other uncontrollable causes.

T5: TRANSPORT FEE (Initial Mobilization/ Interim Mobilization/ Demobilization):

# FIRST MOBILIZATION FEE:

Transportation of the rig and equipment to the location, installation of the rig and equipment at the location, laying of 1st quality geomembrane or appropriate equipment to provide sealing under the diesel tanks, excavation of side and front holes and placement of pipes, installation of the living camp, submission of the inspection report of the drill string to be used and all parts of the rig to the Operator, rig acceptance tests, etc. The fee for the fulfillment of the Contractor's obligations up to the start of the operation fee. It will be offered as a lump sum. The Contractor shall not use any material that has not been inspected.  The first mobilization fee shall be paid in the first progress payment after the rig is made ready for drilling and accepted with a written report after the rig is transported from the site belonging to the Contractor to the location to be shown by the Contractor and assembled (mobilization).

DEMOBILIZATION FEE:

The demobilization decision shall be notified to the Contractor by the Operator within a reasonable time before the end of the contract period. The final demobilization is not included in the total duration of the work.

After the completion of drilling activities in the last location where the rig is located, after the string dismantling, cleaning of mud tanks, wellhead dismantling, environmental and location cleaning and after the location delivery report is signed, the demobilization fee offered as a lump sum is paid.

However, in the event that the Contractor continues to operate the rig in the contract in force with the Operator with a new contract to be signed with the Operator, the Contractor cannot claim the demobilization fee of the contract in force and accepts and undertakes that the relevant fee will not be paid by the Operator.

Mobilization fee of the New Contract is earned with the first Spud of the rig in the new period, following the signing of the contract, and is paid to the Contractor.

The Mobilization fee of the New Contract shall be earned and paid to the Contractor with the first spud of the rig in the new period following the signing of the contract.

In the event that the contract expires and no contract is signed/not signed for the new tender period, if the Contractor leaves the location properly, the demobilization fee in the contract in force will be earned and paid to the Contractor.

# In the event of an increase in fuel prices and an increase in the transportation coefficient, no payment will be made for Mobilization, Demobilization and Intermediate transports under the name of fuel price difference or any other name.

# INTERMEDIATE (INTER)MOBILIZATION FEE:

Upon completion of the drilling program of the first well, the T1 fee is end and the rig is released. From this time onwards, the rig will be dismantled, and the Contractor's and Operator's materials, chemicals, equipment and fuel oil will be transported to the next well and assembled. Transportation of all materials of the Operator and 3rd Party Companies providing services on behalf of the Operator’s materials up to a maximum of 5 loads the responsibility of the Contractor and its fee is included in the quoted price. The fee to be paid for the intermobilization work covering all these activities until the drilling starts in the new well is earned with the spud and paid as a lump sum. This fee also includes the Contractor's dismantling of the rig from the previous location and the cleaning of its waste. Following the elimination of the non-conformities detected for the rigs where spud was not given due to deficiency as a result of the first meeting of the spud commission for the relevant intermobilization, if the spud commission is called for the second time, the unproductive time spent in the process of collecting the commission for the second time, transferring it to the location for spud checks and repeating the checks will be the responsibility of the Contractor. The Contractor will not be able to make any fee, claims etc. Inter-provincial transportation will be made by the shortest State Highway. The transportation numbers specified in the Unit Price Offer Schedule are estimated and may vary. However, the bids of the tenderers will be evaluated on the basis of the specified number of shipments. The offers given in the unit price bid sheet for intermobilization are valid for the distance between 0-50 km (rig shifting is not included in this scope). For intermobilization distances of 51 km and above, the intermobilization fee is determined according to the fee table below and paid to the Contractor:

| Intermobilization Distance | Calculation Method |
| --- | --- |
| 0-50 km | X (intermobilization fee offered in the Unit Price List) is paid. |
| 51-100 km | 1.2 X is paid. (The intermobilization fee offered in the Unit Price List is multiplied by 1.2) |
| 101-200 km | 1.3 X is paid. (The intermobilization fee offered in the Unit Price List is multiplied by 1.3) |
| 201-400 km | 1.5 X is paid. (The intermobilization fee offered in the Unit Price List is multiplied by 1.5) |
| 401 km and above | If the intermobilization exceeds 400 km, in addition to the 1.5 X fee, a surcharge of X/400 per km is payable for the part exceeding 400 km. |

# RIG SHIFT FEE:

# In case the rig at the same location or 0-200 meters from the celler is shifted upon the written instruction of the Operator, 50% of the “0-50 km Intermobilization Fee offered in the unit price list is paid to the Contractor.

# Rounding Time

For wages payable in day units, working hours less than one day shall be divided by 48 and the half-hourly rate shall be calculated and paid. Time intervals below half an hour are rounded up to the nearest half hour.

ANNEX "E"-SERVICE-FEE TABLE

| No. | SERVICE - OPERATION | T1 | T2 | T3 | T4 | T5 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | FIRSTMOBILITY/INTERMEDIATE MOBILITY/DEMOBILITY |  |  |  |  |  |
| 1.1 | Initial mobilization, getting the rig ready for drilling before the start of drilling. |  |  |  |  | X |
| 1.2 | Intermediate Mobilization (Rig transport between locations) |  |  |  |  | X |
| 1.3 | Demobilization |  |  |  |  | X |
| 2 | DRILLING |  |  |  |  |  |
| 2.1 | Drilling (including string building, dismantling, cleaning of tanks up to 6 hours) | X |  |  |  |  |
| 3 | DRILLING MANEUVER |  |  |  |  |  |
| 3.1 | Maneuvers during the addition and removal of drill pipe and other necessary equipment, including descent, ascent and short maneuvers (except in cases of repair, evacuation, etc.) | X |  |  |  |  |
| 3.2 | Reamer roller changes during drilling | X |  |  |  |  |
| 3.3 | Maneuvers during the installation of a rubber casing for the string | X |  |  |  |  |
| 4 | REAMING |  |  |  |  |  |
| 4.1 | Reaming maneuvers | X |  |  |  |  |
| 5 | WELL EXPANSION |  |  |  |  |  |
| 5.1 | Well expansion equipment additions and maneuvers | X |  |  |  |  |
| 6 | CORE DRILLING |  |  |  |  |  |
| 6.1 | Coring operation, well extension and equipment installation | X |  |  |  |  |
| 7 | CORE DRILLING OPERATION | T1 | T2 | T3 | T4 | T5 |
| 7.1 | Core recovery maneuver | X |  |  |  |  |
| 7.2 | Maneuvering with magnet for well cleaning before coring operation | X |  |  |  |  |
| 7.3 | Magnet maneuvering with wireline for well cleaning before coring operation | X |  |  |  |  |
| 7.4 | Exit for coring operation | X |  |  |  |  |
| 7.5 | Core recovery | X |  |  |  |  |
| 7.6 | Core drill disassembly or core drill maintenance if coring will be taken again | X |  |  |  |  |
| 8 | TESTS |  |  |  |  |  |
| 8.1 | Installation of test equipment | X |  |  |  |  |
| 8.2 | Maneuvering for test operation | X |  |  |  |  |
| 8.3 | First two days of test operation | X |  |  |  |  |
| 8.4 | If the test duration is more than two days (well flow test) |  | X |  |  |  |
| 8.5 | Post-test string formation and well control maneuvers | X |  |  |  |  |
| 8.6 | Drill exit maneuver and disassembly for test operation | X |  |  |  |  |
| 9 | LOG OPERATION |  |  |  |  |  |
| 9.1 | Log operation without drill string | X |  |  |  |  |
| 9.2 | Log operation through the drill string | X |  |  |  |  |
| 9.3 | Deviation measurement through the drill string | X |  |  |  |  |
| 9.4 | Wire-line measurements through the drill string | X |  |  |  |  |
| 9.5 | Well cleaning and mud reclamation before log operation | X |  |  |  |  |
| 10 | CASING LOWERING AND CEMENTING |  |  |  |  |  |
| 10.1 | Preparation of casing lowering equipment and rig platform before casing lowering (up to 2 hours) | X |  |  |  |  |
| 10.2 | Preparation of casing lowering equipment and rig platform before casing lowering (Contractor will not be paid for the time exceeding 2 hours) | - | - | - | - | - |
| 10.3 | Maneuvers for well control before casing operation | X |  |  |  |  |
| 10.4 | Casing lowering | X |  |  |  |  |
| 10.5 | Circulation after casing lowering, connection and testing of cement lines, cement preparation and cement operation | X |  |  |  |  |
| 10.6 | Cleanup after cement operation | X |  |  |  |  |
| 10.7 | Log operation through casing | X |  |  |  |  |
| 10.8 | Waiting for cement to freeze | X |  |  |  |  |
| 10.9 | Wellhead construction and pressure tests | X |  |  |  |  |
| 10.10 | Connection of BOPs and pressure and function tests | X |  |  |  |  |
| 10.11 | Lowering for cement drilling and cement drilling | X |  |  |  |  |
| 11 | PRODUCTION TEST |  |  |  |  |  |
| 11.1 | Tests and production operations (packer placement, chemical injections other than acid) | X |  |  |  |  |
| 11.2 | Tests and production operations required by the Operator, while the rig engines are running (tubing maneuvers) | X |  |  |  |  |
| 11.3 | Testing and production operations : -flow measurements - pressure build up a- First two days b-After two days | X | X |  |  |  |
| 11.4 | Tubing inlet or outlet | X |  |  |  |  |
| 12 | MUD PREPARATION, TREATMENT AND CIRCULATION | T1 | T2 | T3 | T4 | T5 |
| 12.1 | Mud reclamation with the drill on the bottom (including maneuvering times) | X |  |  |  |  |
| 12.2 | Dropping cement plugs, mud plugs into the well (including maneuvering times) | X |  |  |  |  |
| 12.3 | Non-Contractor-induced waits after the above operations |  | X |  |  |  |
| 12.4 | Circulation | X |  |  |  |  |
| 12.5 | Mud preparation, treatment and mixing in surface tanks (Except 12.7) | X |  |  |  |  |
| 12.6 | Up to 3 days in total preparation of the rig and mud for petroleum-diesel-synthetic based mud | X |  |  |  |  |
| 12.7 | For petroleum-diesel-synthetic based mud, the Contractor will not be paid for the time exceeding 3 days in the total preparation process of the rig and mud. | - | - | - | - | - |
| 12.8 | After all necessary preparations of petroleum-diesel-synthetic based mud are completed and the operation is started, the related mud is used per day | One hundred and ten percent of the operating fee (110% of T1) |  |  |  |  |
| 12.9 | Up to 3 days for rig daily fee for the cleaning process of petroleum-diesel-synthetic based mud |  | X |  |  |  |
| 12.10 | During the cleaning process of petroleum-diesel-synthetic based mud, the Contractor will not be paid for the period exceeding 3 days for the rig daily fee. | - | - | - | - | - |
| 13 | FISHING |  |  |  |  |  |
| 13.1 | Except for Article 15.1.3 of the Contract, the duration of the Fishing operations (The Operator determines the methods and duration of the Fishing operations) In case of waiting, repairs or force majeure during the Fishing, each tariff fee is applied according to the tariff in this document (e.g., 90% of the T1 tariff during the fishing, in case of waiting with the team during the Fishing; 90% of the offered T1 and in case of repair during the Fishing 85% of the offered T1) | Eighty-five percent of the operating fee (85% of T1) |  |  |  |  |
| 14 | REPAIRS AND MAINTENANCE |  |  |  |  |  |
| 14.1 | Routine maintenance that will not interrupt the operation (0.5 hours per day) | X |  |  |  |  |
| 14.2 | All lost time (including all processes such as changes, maneuvers, etc.) due to repair, maintenance, parts replacement, spare parts, etc. (up to 24 hours in a calendar month) |  |  | X |  |  |
| 14.3 | All of the lost time (including all processes such as changes, maneuvers, etc.) due to repair, maintenance, parts replacement, spare parts, etc. (The Contractor is not paid for periods exceeding 24 hours in a calendar month and for periods exceeding 4 hours in a calendar day) | - | - | - | - | - |
| 14.4 | Drill string shifting up to 0.5 hours | X |  |  |  |  |
| 14.5 | The Contractor will not be paid for the time exceeding 0.5 hours for drill rope shifting | - | - | - | - | - |
| 14.6 | Drill rope “shifting + cutting” up to 2 hours | X |  |  |  |  |
| 14.7 | No fee is paid to the Contractor for periods exceeding 2 hours for cutting the drill rope | - | - | - | - | - |
| 14.8 | First test of wellhead equipment | X |  |  |  |  |
| 14.9 | If the wellhead equipment fails the first test, the Contractor will not be paid for the time until the test is successfully performed | - | - | - | - | - |
| 14.10 | Replacement of pump liners in accordance with the well program and consequent cessation of operations | X |  |  |  |  |
| 14.11 | Placing BOPs that are not in the program or replacing their spares as instructed by the Operator | X |  |  |  |  |
| 15 | VARIOUS STANDBY | T1 | T2 | T3 | T4 | T5 |
| 15.1 | Waiting due to stoppage of work on the rig due to deterioration in the physical condition of the rig concrete, location and road during drilling |  |  |  | X |  |
| 15.2 | All kinds of waiting (decision etc.) with the instruction of the Operator, whether or not there is a drill string in the well, whether or not circulation is made in the well |  | X |  |  |  |
| 15.3 | Standby due to adverse weather conditions as instructed by the Operator Representative |  |  |  | X |  |
| 15.4 | Waiting due to work accidents and/or legal proceedings that will stop the business |  |  |  | X |  |
| 15.5 | No payment shall be made for waiting due to any type of drilling water supply disruptions caused by the Contractor. | - | - | - | - | - |
| 15.6 | Delays due to location waiting caused by the Operator | Fifty percent of the operating fee (50% of T1) |  |  |  |  |
| 15.7 | Waiting due to delays caused by other service companies provided by the Operator |  | X |  |  |  |
| 15.8 | Waiting due to delays caused by other service companies provided by the Contractor shall not be charged. | - | - | - | - | - |
| 15.9 | No fee is paid for waiting due to delays caused by the Contractor. | - | - | - | - | - |
| 15.10 | Waiting for the supply of materials or personnel required to be supplied by the Operator and their transportation to the rig |  | X |  |  |  |
| 15.11 | During casing lowering (in case the casing lowering equipment is provided by the Contractor, the Operator or the subcontractor of the Contractor), the Contractor shall not be paid for the time loss period to be observed and decided by the Representative of the Operator due to reasons such as thread grabbing, failure to center the casing (due to rig plumb setting or independent of plumb setting), worker error, slow work of the personnel, power tong operator use error, etc. | - | - | - | - | - |
| 15.12 | In the event that wellhead construction, dismantling, pressure/function tests, string construction, dismantling, etc. exceed the time periods determined according to the industry standards, the Contractor shall not be paid for the time exceeded (maximum 24 hours for wellheads with a diameter of 13-5/8" and below, maximum 36 hours for wellheads with a diameter of 21 1/4" and above, no fee shall be paid to the Contractor for the loss of time for string construction-dismantling to be observed and decided by the Operator Representative). | - | - | - | - | - |
| 15.13 | When an equipment or material that does not meet the contract conditions is used, the Contractor shall not be paid for the lost time due to the relevant material or equipment. | - | - | - | - | - |
| 15.14 | The Contractor shall not be paid for the waiting period due to the inability to install the water line before or after the spud, late installation or malfunctions that may occur in the operating water line (tears, punctures, cracks, etc. in the water line). | - | - | - | - | - |
| 15.15 | In case of replacement (for all rig components) due to malfunction, incompatibility, recurring problems, the Contractor shall not be paid for the replacement period. | - | - | - | - | - |
| 15.16 | Waiting due to any service-services-materials-equipment provided by the Contractor or the Contractor's Subcontractor | - | - | - | - | - |